## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Group41 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Yujia Zhong | Junqi Si | Ming Chen | Kesai Ji
Project Start Date: | 14/09/2021 |  |  |  |  | December | [13 empty] | January | [27 empty] | February
Scrolling Increment: | 0 | time axis 2021-12-22 to 2022-02-15
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-12-22 to 2022-02-15
Interation01
Task | Goal | Name | 25% | 2021-12-22 | 3 | 2021-12-22: 2; 2021-12-23: 2; 2021-12-24: 2
Lead and manage | Milestone | Ming Chen |  | 2021-12-27 | 1 | bar: 2021-12-26 to 2021-12-29
Communicate and master | Low Risk | Yujia Zhong | 50% | 2021-12-19 | 10
Focus on project quality | Milestone | Kesai Ji |  | 2022-01-11 | 1 | bar: 2022-01-11
solve the problem | Med Risk | Junqi Si | 10% | 2021-12-28 | 6
Interation02
Ensure project stability | High Risk | JUnqi Si | 60% | 2021-12-28 | 13
Project sensitive Mastery | On Track | Ming Chen | 50% | 2021-12-30 | 9
Carry out high creation | Low Risk | Junqi Si | 33% | 2022-01-04 | 11
Perfect web page | Milestone | Kesai Ji |  | 2022-01-06 | 1 | bar: 2022-01-06
Interation03
Check the result | On Track | Kesai Ji |  | 2022-01-06 | 4
Focus on project safety | Med Risk | Ming Chen |  | 2022-01-09 | 14
Carry on high creation | On Track | Junqi Si |  | 2022-01-24 | 6
Develop | Goal | Yujia Zhong |  | 2022-01-28 | 3 | 2022-01-28: 2; 2022-01-29: 2; 2022-01-30: 2
TITLE 4
Task 1 |  |  |  | 2022-01-31 | 15
Task 2 |  |  |  | 2022-02-14 | 5
Task 3 | Milestone |  |  | 2022-03-28 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one
Formulas:
Kesai Ji = [Kesai Ji, row above]+2

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-12-22 |  |  |  |  | December | [13 empty] | January | [27 empty] | February
Scrolling Increment: | 1 | time axis 2021-12-23 to 2022-02-16
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2021-12-22 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2021-12-27 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2021-12-19 | 10
Task 4 | Milestone |  |  | 2022-01-11 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2021-12-28 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-12-28 | 13
Task 2 | On Track |  | 50% | 2021-12-30 | 9
Task 3 | Low Risk |  | 33% | 2022-01-04 | 11
Task 4 | Milestone |  |  | 2022-01-06 | 1 | bar: T
Task 5 |  |  |  | 2022-01-07 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-01-06 | 4
Task 2 | Med Risk |  |  | 2022-01-09 | 14
Task 3 | On Track |  |  | 2022-01-24 | 6
Task 4 | Goal |  |  | 2022-01-28 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2021-12-28 | 19
TITLE 4
Task 1 |  |  |  | 2022-01-31 | 15
Task 2 |  |  |  | 2022-02-14 | 5
Task 3 | Milestone |  |  | 2022-03-28 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-12-22 |  |  |  |  | December | [6 empty] | January | [34 empty] | February
Scrolling Increment: | 5 | time axis 2021-12-27 to 2022-02-20
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-12-27 to 2022-02-20
TITLE 1
Task 1 | Goal | Name | 25% | 2021-12-22 | 3
Task 2 | Milestone |  |  | 2021-12-27 | 1 | bar: 2021-12-27
Task 3 | Low Risk |  | 50% | 2021-12-19 | 10
Task 4 | Milestone |  |  | 2022-01-11 | 1 | bar: 2022-01-11
Task 5 | Med Risk |  | 10% | 2021-12-28 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-12-28 | 13
Task 2 | On Track |  | 50% | 2021-12-30 | 9
Task 3 | Low Risk |  | 33% | 2022-01-04 | 11
Task 4 | Milestone |  |  | 2022-01-06 | 1 | bar: 2022-01-06
Task 5 |  |  |  | 2022-01-07 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-01-06 | 4
Task 2 | Med Risk |  |  | 2022-01-09 | 14
Task 3 | On Track |  |  | 2022-01-24 | 6
Task 4 | Goal |  |  | 2022-01-28 | 3 | 2022-01-28: 2; 2022-01-29: 2; 2022-01-30: 2
Task 5 | Low Risk |  |  | 2021-12-28 | 19
TITLE 4
Task 1 |  |  |  | 2022-01-31 | 15
Task 2 |  |  |  | 2022-02-14 | 5
Task 3 | Milestone |  |  | 2022-03-28 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one